## 1-A General Conditions
Boston University
ITB Attachment 1-A - General Conditions Breakdown
School of Theater 4th Floor
School of Visual Arts 5th Floor
|  |  | Construction |  | Close out
| Position/Name | Hourly Rate | May | June | July | Total
Example | Project Manager | 100 | 42 | 42 | 15 | 99
| Jim Jones |  |  |  |  | 9900
1 | Executive Management | 205 | 8 | 8 | 2 | 18
| Adam Arsenault |  |  |  |  | 3690
2 | Senior Project Manager | 0 |  |  |  | 0
| Rob McLean |  |  |  |  | 0
3 | Project Manager | 120 | 48 | 48 | 12 | 108
| Chris Flynn |  |  |  |  | 12960
4 | Project Engineer | 90 | 32 | 32 | 8 | 72
| Isabelle Toth |  |  |  |  | 6480
5 | Superintendent | 122.5 | 160 | 160 | 40 | 360
| Cameron Tetreault |  |  |  |  | 44100
6 | Superintendent | 122.5 |  |  |  | 0
| Christian Mascaro |  |  |  |  | 0
7 | Position | 0 |  |  |  | 0
| Name |  |  |  |  | 0
8 | Position | 0 |  |  |  | 0
| Name |  |  |  |  | 0
9 | Position | 0 |  |  |  | 0
| Name |  |  |  |  | 0
| Total General Conditions |  |  |  |  | 67230

## 1-B General Requirements - 4th
Boston University
ITB Attachment 1-B - General Requirements Breakdown
School of Theater 4th Floor
Description | Cost per Week | No. of Weeks | Total Cost
Mobilize/Demobilize |  |  | N/A
Temporary Utilities & Facilities |  |  | 1260
Reproduction - Drawings/Printing |  |  | 150
Project Temporary Signage |  |  | 850
Mail/Postage |  |  | Included
Field Computers/Software |  |  | 900
Field Office Supplies |  |  | 1250
Field Office Equipment |  |  | 2700
Field Office Furniture |  |  | Included
Misc. Supplies (Final Clean) |  |  | 952
Cellphones - Field Personnel |  |  | Included
Parking | 70 | 9 | 630
Safety Equipment& Signage |  |  | 125
| TOTAL |  | 8817

## 1-B General Requirements - 5th
Boston University
ITB Attachment 1-B - General Requirements Breakdown
School of Visual Arts 5th Floor
Description | Cost per Week | No. of Weeks | Total Cost
Mobilize/Demobilize |  |  | N/A
Temporary Utilities & Facilities |  |  | 1260
Reproduction - Drawings/Printing |  |  | 150
Project Temporary Signage |  |  | 850
Mail/Postage |  |  | Included
Field Computers/Software |  |  | 900
Field Office Supplies |  |  | 1250
Field Office Equipment |  |  | 2700
Field Office Furniture |  |  | Included
Misc. Supplies (Final Clean) |  |  | 1201
Cellphones - Field Personnel |  |  | Included
Parking | 70 | 9 | 630
Safety Equipment& Signage |  |  | 125
| TOTAL |  | 9066