## Instructions
WATERTOWN MALL REPOSITIONING PROJECT
Bid Pricing Workbook ¦ 550 Arsenal Street, Watertown, Massachusetts 02472
Bidder Information
Bidder Company | New England Construction |  | Completion order: 1 Instructions 2 Allowances-Alternates 3 Three SOVs 4 GC-GR 5 Support Tabs 6 Document Register 7 Bid Summary
Primary Contact | Adam Arsneault
Email | aarsenault@neconstruction.com
Phone | (401) 434 0112
Proposal Date | 2026-08-14
Bid Valid Through | 2026-09-14
Bid Administration
Bid Package Issued | 2026-07-17 | Submit electronically to dave@citylightsdev.com. Use subject: “Watertown Mall Repositioning Project - Bid Submission - [Contractor Name].” All questions and site-visit requests shall be directed only to David Roache.
Individual Site Visits | July 20-29, 2026, by appointment
Bidder Questions Due | 2026-08-03
Responses Issued | 2026-08-06
Bid Due | Friday, August 14, 2026, close of business
Workbook Completion Instructions
1 | Complete all yellow cells with blue text. Do not overwrite formula cells.
2 | Provide one combined GMP under a single contract, with three separate trade-level SOVs: Base Building / Core & Shell / Site, Joyful Garden Tenant Fit-Out, and Burlington Coat Factory Conceptual Fit-Out.
3 | Trade line items on each SOV must exclude allowances listed separately on the Allowances-Alternates tab to avoid double counting.
4 | Complete the GC-GR allocation so every general-condition/general-requirement item is allocated 100% among the three scopes. If Fixed, use one line and identify time period.
5 | List all qualifications, assumptions, and exclusions on the Q-A-E tab. Statements appearing only in a cover letter may be disregarded during leveling.
6 | Provide all requested unit costs, subcontractors, schedule milestones, logistics narratives, and document acknowledgments.
7 | Alternates are excluded from the base GMP unless specifically marked Included in Base = Yes.
8 | Return this workbook in editable Excel format with the complete proposal.
Color Legend
Yellow / Blue Text | Bidder input
Green Text | Formula linked from another worksheet
Black Text | Formula calculated on the same worksheet
Light Green Fill | Subtotal or total

## Allowances-Alternates
ALLOWANCES AND ALTERNATES
Enter all allowances and alternates separately. Do not duplicate these amounts in trade SOV line items. These allowances are suggested, please identify any other allowances assumed.
Allowance Summary by Scope
Scope | Included Allowances ($) | Bidder Notes | Status
Base Building | 123650 |  | Complete
Joyful Garden | 872059 |  | Complete
Burlington | 63000 |  | Complete
Allowances Included in Base Bid
Allowance No. | Scope | Cost Code | Description | Qty | Unit | Unit Cost | Amount | Basis / Included Scope | Notes
A-01 | Base Building | 02-8900 | Presumed ACM allowance | 1 | TBD | 90150 | 90150 | Include containment, removal, disposal, monitoring coordination, permits, testing coordination, and restoration.
A-02 | Base Building | 02-4119 | GPR scanning of existing slab | 1 | LS | 3000 | 3000 | Carry as a separate allowance pending final scanning scope.
A-03 | Base Building | 05-5000 | Temporary structural support at loading dock opening | 1 | LS | 10000 | 10000 | Quantity and fully burdened unit cost required.
A-04 | Base Building | 05-5000 | Temporary structural support at Burlington front entrance | 1 | LS | 18000 | 18000 | Quantity and fully burdened unit cost required.
A-05 | Base Building | 05-5000 | Temporary structural support at Joyful Garden opening | 1 | LS | 2500 | 2500 | Quantity and fully burdened unit cost required.
A-06 | Joyful Garden | 09-5100 | Cove/acoustic ceiling grid detailing allowance | 1 | LS | 50000 | 50000 | Complete acoustic material system; not wood-based.
A-07 | Joyful Garden | 26-0000 | Architectural and decorative lighting allowance | 1 | LS | 40000 | 40000 | Base design prior to selected VE alternates.
A-08 | Joyful Garden | 06-2000 | Custom millwork surround allowance | 1 | LS | 25000 | 25000 | Include framing, finish material, lighting coordination, supports, and shop drawings.
A-09 | Joyful Garden | 11-3100 | Boston Showcase kitchen-equipment allowance | 1 | LS | 757059 | 757059 | Boston Showcase is required kitchen-equipment subcontractor/vendor.
A-10 | Burlington | 60-0000 | Conceptual design-development allowance | 1 | LS | 0 | 0 | Identify scope and basis; do not combine with pricing contingency.
A-11 | Burlington | 02-8900 | Presumed ACM allowance within Burlington space | 1 | TBD | 0 | 0 | Subject to Axiom follow-up survey after Carter's vacancy. | In base building scope
A-12 | Burlington | 03-3500 | Floor grinding / slab preparation allowance | 1 | LS | 63000 | 63000 | Identify assumed quantity and unit cost.
0
A-13 | Base Building |  | Additional Work scope at Target | 1 | LS |  | 0
0
0
0
0
0
0
0
0
Alternates - Excluded from Base GMP Unless Marked Otherwise
Alternate No. | Scope | Cost Code | Description | Add / Deduct | Amount | Included in Base? | Schedule Impact (Days) | Basis | Notes
ALT-01 | Joyful Garden | 10-2200 | Fabric finish at movable partitions in lieu of base vinyl | Add | 68000 | No | 0
ALT-02 | Joyful Garden | 09-3000 | Paint columns in lieu of tile finish | Deduct |  | No | 0
ALT-03 | Joyful Garden | 26-5100 | Lighting VE alternate - reduced architectural/decorative fixture package | Deduct |  | No | 0
ALT-04 | Joyful Garden | 23-0000 | Standard return grilles with linear supply diffusers | Deduct |  | No | 0
ALT-05 | Joyful Garden | 23-0000 | Standard supply diffusers and return grilles | Deduct |  | No | 0
ALT-06 | Joyful Garden | 23-0000 | Transformer-room transfer/exhaust approach in lieu of heat pump | Deduct |  | No | 0
ALT-07 | Joyful Garden | 11-0000 | Projectors and screens | Add | 18900 | No | 0
ALT-08 | Joyful Garden | 12-0000 | Approved-equal center-bar wall surface solid-surface material | Deduct |  | No | 0

## GC-GR
GENERAL CONDITIONS AND GENERAL REQUIREMENTS
Enter quantity and unit cost. Allocate every line item 100% among the three scopes. Contractor may utilize this sheet as necessary. If Fixed GCs and GRs are preferred, enter the costs on the appropriate line and omit detail. Identify the assumed time period for each in the notes.
Cost Code | Description | Qty | Unit | Unit Cost | Total | Base % | Base $ | JG % | JG $ | BCF % | BCF $ | Notes
50-0100 | Project Executive | 240 | HR | 205 | 49200 | 25% | 12300 | 40% | 19680 | 35% | 17220
50-0200 | Project Manager | 960 | HR | 120 | 115200 | 25% | 28800 | 40% | 46080 | 35% | 40320
50-0300 | Superintendent | 2560 | HR | 155 | 396800 | 25% | 99200 | 40% | 158720 | 35% | 138880
50-0310 | Assistant Superintendent | 160 | HR | 105 | 16800 | 25% | 4200 | 40% | 6720 | 35% | 5880
50-0400 | Project Engineer / APM | 780 | HR | 90 | 70200 | 100% | 70200 | 0% | 0 | 0% | 0
50-0500 | Safety Manager / Safety Program | 84 | HR | 175 | 14700 | 25% | 3675 | 40% | 5880 | 35% | 5145
50-0600 | Scheduler / Schedule Updates |  | HR |  | 0 |  | 0 |  | 0 |  | 0
50-0700 | Accounting / Project Administration | 84 | WK | 450 | 37800 | 25% | 9450 | 40% | 15120 | 35% | 13230
50-1000 | Mobilization / Demobilization | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
50-1100 | Temporary Office / Field Facilities |  | MO |  | 0 |  | 0 |  | 0 |  | 0
50-1200 | Temporary Utilities |  | MO |  | 0 |  | 0 |  | 0 |  | 0
50-1300 | Temporary Heat / Ventilation |  | MO |  | 0 |  | 0 |  | 0 |  | 0
50-1400 | Temporary Lighting / Power |  | MO |  | 0 |  | 0 |  | 0 |  | 0
50-1500 | Temporary Partitions / Dust Protection | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
50-1600 | Occupied-Mall Fire / Life Safety Measures | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
50-1700 | Security / Access Control |  | MO |  | 0 |  | 0 |  | 0 |  | 0
50-1800 | Fencing / Barricades / Site Signage | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
50-1900 | Hoisting / Lifts / Material Handling | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
51-0100 | Layout / Survey / Field Engineering | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
51-0200 | Testing / Inspections Not Included Elsewhere | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
51-0300 | Submittals / BIM / Coordination | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
51-0400 | Permitting Administration | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
51-0500 | Meetings / Reporting / Photography |  | MO |  | 0 |  | 0 |  | 0 |  | 0
51-0600 | Closeout / As-Builts / O&M Manuals | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
55-0100 | Daily Labor |  | HR |  | 0 |  | 0 |  | 0 |  | 0
55-0200 | Cleaning |  | WK |  | 0 |  | 0 |  | 0 |  | 0
55-0300 | Dumpsters / Disposal Not in Trade Scope |  | MO |  | 0 |  | 0 |  | 0 |  | 0
55-0400 | Snow / Weather Protection | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
55-0500 | After-Hours / Phasing Premium | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
55-0600 | Small Tools / Consumables | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
55-0700 | Parking / Travel / Delivery Coordination | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
55-0800 | Other GC / GR | 1 | LS
| Fixed GCs |  | LS
| Fixed GRs | 1 | LS | 101028 | 101028 | 58% | 58596.24 | 25% | 25257 | 17% | 17174.76
GC / GR Total |  |  |  |  | 801728 |  | 286421.24 |  | 277457 |  | 237849.76
Allocation Check | [5 empty] | Base % |  | JG % |  | BCF % |  | Total Allocation
All GC / GR dollars allocated | [6 empty] | 286421.24 |  | 277457 |  | 237849.76 | 0

## Base Building SOV
BASE BUILDING / CORE & SHELL / SITE SOV
Trade amounts exclude allowances, GC/GR, contingencies, insurance, bonds, fee, and permits.
CSI / Cost Code | Cost Category | Detailed Scope Description | Proposed Subcontractor / Vendor | Bid Amount | Notes / Qualifications
01 - General Requirements Included Within Trade Scope
01-0000 | Trade General Requirements | Trade-specific mobilization, supervision, submittals, closeout, protection, and coordination not included on GC-GR tab. | New England Construction | 26775
02 - Existing Conditions
02-4119 | Selective Demolition | Complete selective demolition for base building, mall corridor, Target entry closure, loading dock, facades, utilities, and related areas. | TBD | 223940
02-8900 | Hazardous Materials Abatement | Confirmed ACM and other hazardous-material work assigned to Base Building, excluding separately listed presumed-ACM allowance. | TBD | 175000
03 - Concrete
03-1000 | Concrete | Foundations, slab removal and replacement, curbs, pads, pits, patching, and related work. | TBD | 169025
03-3500 | Concrete Finishing | Grinding, leveling, finishing, and preparation assigned to Base Building. | TBD | 0 | Floor prep as required with flooring
04 - Masonry
04-0000 | Masonry | New and infill masonry, repairs, lintels, reinforcing, patching, and related work. | TBD | 36625
05 - Metals
05-5000 | Structural Steel & Misc. Metals | Structural steel, temporary support, miscellaneous metals, supports, rails, embeds, and related work. | TBD | 202300
06 - Wood, Plastics and Composites
06-1000 | Rough Carpentry | Blocking, plywood, curbs, backing, temporary carpentry, and related work. | TBD | 1875 | most work with the trades
06-2000 | Finish Carpentry | Finish carpentry and millwork included in Base Building. | TBD | 0 | No finish carpentry
07 - Thermal and Moisture Protection
07-1000 | Waterproofing / Sealants | Waterproofing, caulking, sealants, firestopping, and related work. | TBD |  | With the trades
07-2400 | EIFS | Exterior insulation and finish systems. | TBD |  | See Burlington scope
07-4600 | Siding / Exterior Cladding | Exterior cladding, panels, flashings, and accessories. | TBD |  | See Burlington scope
07-5000 | Membrane Roofing | Roofing, curbs, penetrations, patching, warranties, and required roofer coordination. | TBD | 107100
08 - Openings
08-1000 | Doors, Frames & Hardware | Doors, frames, hardware, access doors, and related work. | TBD | 15980
08-3000 | Specialty / Overhead Doors | Overhead doors, specialty doors, operators, and related systems. | TBD | 18000
08-4000 | Glass & Glazing | Storefront, curtain wall, glazing, entrance systems, and associated metals. | TBD |  | See Burlington & Joyful scope
09 - Finishes
09-2000 | Drywall & Metal Framing | Partitions, soffits, ceilings, enclosures, rated assemblies, and patching. | TBD | 202357
09-5100 | Acoustical Ceilings | Acoustical ceilings and related grid systems in Base Building areas. | TBD | 24350
09-6000 | Flooring | Flooring, base, preparation, transitions, and related work. | TBD | 19532
09-9100 | Painting & Coating | Interior and exterior painting, coatings, exposed-structure painting, and touch-up. | TBD | 21165
10 - Specialties
10-0000 | Miscellaneous Specialties | Toilet partitions, accessories, extinguishers, signage supports, wall protection, and related specialties. | TBD |  | See Burlington & Joyful scope
11 - Equipment
11-1000 | Vehicle / Pedestrian Equipment | Dock equipment, lifts, bollards, gates, and related equipment. | TBD | 42000
21-28 - MEP / FP / Low Voltage
21-0000 | Fire Protection | Fire-protection demolition, new work, controls, testing, and permits. | TBD | 247700
22-0000 | Plumbing | Plumbing demolition, underground work, water, sanitary, gas, and related coordination. | TBD | 39000
23-0000 | HVAC | HVAC demolition, rooftop equipment, ductwork, controls, testing, balancing, and roofing coordination. | TBD | 236250
26-0000 | Electrical | Electrical demolition, service, distribution, lighting, power, grounding, and controls. | TBD | 253818
27-0000 | Telecom / AV | Telecom and AV infrastructure included in base-building documents. | TBD |  | Included
28-0000 | Fire Alarm / Security | Fire alarm and security demolition, new work, testing, and permits. | TBD |  | Included
31-33 - Site and Exterior Work
31-0000 | Earthwork / Sitework | Site demolition, earthwork, utilities, erosion control, trenching, and restoration. | TBD | 330132
32-0000 | Exterior Improvements / Landscape | Paving, curbing, sidewalks, landscape, site furnishings, striping, and related work. | TBD | 195743
33-0000 | Site Utilities | Storm, sanitary, water, gas, electrical site utilities, testing, and connections. | TBD |  | Included
Other
10-1400 | Signage & Graphics | Only signage and graphics shown in bid documents; identify owner-direct signage excluded.
Trade Subtotal (excluding separately listed allowances) |  |  |  | 2588667
Allowances Included in Base Bid |  |  |  | 123650
Direct Trade Cost |  |  |  | 2712317
Scope total carried to Bid Summary excludes general conditions, contingencies, insurance, bonds, fee, and permits, which are calculated separately on the Bid Summary and GC-GR tabs. Scope: Base Building.

## Burlington SOV
BURLINGTON COAT FACTORY CONCEPTUAL SOV
Conceptual trade-level estimate for approximately 31,000 SF remaining mall space.
CSI / Cost Code | Cost Category | Detailed Scope Description | Proposed Subcontractor / Vendor | Bid Amount | Notes / Qualifications
01-02 - General Requirements and Existing Conditions
01-0000 | Trade General Requirements | Trade-specific supervision, submittals, coordination, closeout, and protection not included on GC-GR tab. | New England Construction | 34450
02-4119 | Selective Demolition | Complete demolition required for turnkey Burlington prototype fit-out. | TBD | 25435
02-8900 | Hazardous Materials Abatement | Confirmed hazardous-material work; exclude separately listed presumed-ACM allowance. | TBD |  | See base scope
03-05 - Concrete, Masonry and Metals
03-1000 | Concrete Patching | Slab removal, trenching, repair, pits, pads, and related work. | TBD | 21672
03-3500 | Concrete Finishing / Slab Preparation | Grinding, leveling, polishing, moisture mitigation, and preparation for prototype flooring. | TBD |  | see allowances
04-0000 | Masonry | Masonry infill, repair, facade masonry, and related work. | TBD |  | See base scope
05-5000 | Structural Steel & Misc. Metals | Loading dock, facade, RTU, opening, stair, rail, and miscellaneous metal work. | TBD | 146610
06-08 - Carpentry, Envelope and Openings
06-1000 | Rough Carpentry | Blocking, plywood, roof curbs, and backing. | TBD | 4650
06-2000 | Finish Carpentry & Millwork | Prototype millwork and architectural woodwork. | TBD | 30440
07-1000 | Waterproofing / Sealants | Waterproofing, sealants, firestopping, and related work. | TBD |  | In trades
07-2400 | EIFS / Exterior Finish | Prototype facade EIFS and associated systems. | TBD | 92606
07-5000 | Roofing | Roof repair, curbs, penetrations, warranty work, and prototype roof scope. | TBD | 107000
08-1000 | Doors, Frames & Hardware | Interior and exterior doors, frames, hardware, and access doors. | TBD | 47350
08-3000 | Specialty / Overhead Doors | Loading dock doors, security shutters, automatic operators, and specialty doors. | TBD |  | See base scope
08-4000 | Storefront / Glass & Glazing | Prototype storefront, automatic sliding doors, vestibule, glazing, and facade metal. | TBD | 173000
09-12 - Finishes, Specialties and Equipment
09-2000 | Drywall & Metal Framing | Demising walls, partitions, soffits, enclosures, patching, and open-ceiling preparation. | TBD | 487742
09-5100 | Acoustical Ceilings | Back-of-house and other prototype ceilings. | TBD | 6390
09-6000 | Flooring | Prototype flooring, polished concrete, carpet tile, LVT, base, preparation, and transitions. | TBD | 16343
09-9100 | Painting & Coating | Interior/exterior paint and exposed-structure painting. | TBD | 80790
10-0000 | Specialties | Toilet partitions/accessories, wall protection, extinguishers, lockers, and prototype specialties. | TBD | 106752
11-1000 | Dock / Material Handling Equipment | Dock lift, levelers, seals, shelters, and related equipment. | TBD |  | See base scope
12-0000 | Furnishings | Only landlord-provided furnishings required by tenant work letter/prototype. | TBD |  | Not included
21-28 - MEP / FP / Low Voltage
21-0000 | Fire Protection | Prototype fire-protection system, testing, and permits. |  | 18600
22-0000 | Plumbing | Restrooms, janitor closet, water, sanitary, floor drains, equipment, and testing. | TBD | 105000
23-0000 | HVAC | Prototype HVAC systems, controls, distribution, testing, balancing, and warranties. | TBD | 206000
26-0000 | Electrical | Service, distribution, lighting, power, controls, and prototype requirements. | TBD | 465873
27-0000 | Telecom / Low Voltage | Telecom, data, pathways, and related work. | TBD | 37546
28-0000 | Fire Alarm / Security | Fire alarm, security, and required coordination. | TBD | 70849
31-33 - Site / Facade Interfaces
31-0000 | Sitework / Utility Interfaces | Site and utility work specifically attributable to Burlington fit-out. | TBD |  | See base scope
32-0000 | Exterior Improvements | Facade, entrances, loading, sidewalk, paving, and landscape interfaces. | TBD | 12185 | Interior fencing
Other
10-1400 | Signage Infrastructure | Structural supports, conduit, and electrical facilities for tenant signage; exclude tenant sign fabrication unless required. | TBD | 13984
Trade Subtotal (excluding separately listed allowances) |  |  |  | 2311267
Allowances Included in Base Bid |  |  |  | 63000
Direct Trade Cost |  |  |  | 2374267
Scope total carried to Bid Summary excludes general conditions, contingencies, insurance, bonds, fee, and permits, which are calculated separately on the Bid Summary and GC-GR tabs. Scope: Burlington.

## Joyful Garden SOV
JOYFUL GARDEN TENANT FIT-OUT SOV
Based on July 3, 2026 documents, bid assumptions, and anticipated addendum.
CSI / Cost Code | Cost Category | Detailed Scope Description | Proposed Subcontractor / Vendor | Bid Amount | Notes / Qualifications
01-02 - General Requirements and Existing Conditions
01-0000 | Trade General Requirements | Trade-specific supervision, submittals, coordination, closeout, and protection not included on GC-GR tab. | New England Construction | 18475
02-4119 | Selective Demolition | Tenant fit-out selective demolition | TBD | 57250
03-05 - Concrete, Masonry and Metals
03-1000 | Concrete Patching | Subslab trenching, patching, equipment pads, leveling, and related work. | TBD | 66622
04-0000 | Masonry | Masonry work, patching, and infill. | TBD |  | See base scope
05-5000 | Structural Steel & Misc. Metals | RTU supports, equipment supports, bar/ceiling supports, miscellaneous metals, and related work. | TBD |  | See base scope
06 - Carpentry and Millwork
06-1000 | Rough Carpentry | Blocking, backing, plywood, and concealed supports. | TBD |  | With trades
06-2000 | Finish Carpentry & Millwork | Bar, back bar, host stations, server stations, decorative surrounds, shelves, and custom millwork. | TBD | 376016
07-08 - Envelope and Openings
07-1000 | Waterproofing / Sealants | Sealants, waterproofing, firestopping, and related work. | TBD |  | With trades
07-5000 | Roofing | RTU curbs, penetrations, patching, and roofer coordination. | TBD | 51100
08-1000 | Doors, Frames & Hardware | Doors, frames, hardware, access panels, and related work. | TBD | 46870
08-3000 | Specialty Doors / Folding Panels | Folding partitions, pocket/specialty doors, tracks, controls, supports, and accessories. | TBD | 219000
08-4000 | Glass & Glazing | Interior and exterior glazing, storefront, mirrors, and related work. | TBD | 65237
09 - Finishes
09-2000 | Drywall & Metal Framing | Partitions, soffits, cove assemblies, enclosures, ceilings, patching, and backing. | TBD | 201092
09-5100 | Acoustical / Specialty Ceilings | Acoustic cove/grid system, ceilings, suspension, supports, transitions, and accessories. | TBD | 16035 | See allowances for additional coverage
09-6000 | Flooring | Tile, resilient flooring, epoxy flooring, base, preparation, transitions, and protection. | TBD | 238115
09-7200 | Wall Coverings | Wall coverings and associated preparation. | TBD |  | Included in Painting
09-9100 | Painting & Coating | Painting, coatings, painted reveals, restroom paint above tile, and touch-up. | TBD | 121477
10-12 - Specialties, Equipment and Furnishings
10-0000 | Miscellaneous Specialties | Toilet partitions, accessories, wall protection, extinguishers, decorative specialties, and signage. | TBD | 25106
10-2800 | Toilet & Bath Accessories | Restroom accessories, mirrors, dispensers, partitions, and related work. | TBD | 26605
11-3100 | Commercial Kitchen Equipment | Boston Showcase equipment package and all contractor-assigned coordination, installation, rough-ins, connections, supports, protection, and closeout. | TBD |  | See allowances sheet
12-2000 | Window Treatments | Window treatments, tracks, controls, and related work. | TBD |  | Not in scope
12-5000 | Furniture Coordination | Loose tables and chairs are by tenant; include only required coordination and fixed construction. | TBD |  | Coordinating in field with owner - no cost
21-28 - MEP / FP / Low Voltage
21-0000 | Fire Protection | Fire-protection demolition, new work, testing, and permits. | TBD | 85000
22-0000 | Plumbing | Underground waste, water, gas, fixtures, kitchen equipment connections, testing, and permits. | TBD | 648000
23-0000 | HVAC | Consolidated RTUs, ductwork, controls, exhaust, makeup air, testing, balancing, and roofing coordination. | TBD | 470000
26-0000 | Electrical | Lighting, power, equipment connections, lighting controls, plug mold, cove lighting, and testing. | TBD | 583948
27-0000 | Telecom | Telecom cabling, wireless access points, pathways, and terminations. | TBD | 69709
27-4000 | Audio Visual | AV infrastructure and included equipment; projectors only if included by alternate. | TBD | 14000
28-0000 | Security / Fire Alarm | Security and fire-alarm work, testing, and permits. | TBD
Other
Trade Subtotal (excluding separately listed allowances) |  |  |  | 3399657
Allowances Included in Base Bid |  |  |  | 872059
Direct Trade Cost |  |  |  | 4271716
Scope total carried to Bid Summary excludes general conditions, contingencies, insurance, bonds, fee, and permits, which are calculated separately on the Bid Summary and GC-GR tabs. Scope: Joyful Garden.

## Unit Costs
UNIT COSTS
Provide fully burdened unit costs suitable for post-bid reconciliation and change pricing. Identify any other relevant unit costs.
Unit Cost No. | Scope | Cost Code | Description | Unit | Labor | Material | Equipment | OH&P | Total Unit Cost | Notes / Inclusions
UC-01 | Base Building | 02-8900 | ACM floor tile / mastic abatement | SF |  |  |  |  | 0
UC-02 | Base Building | 02-8900 | ACM pipe insulation abatement | LF |  |  |  |  | 0
UC-03 | Base Building | 02-8900 | ACM ceiling material abatement | SF |  |  |  |  | 0
UC-04 | Base Building | 02-8900 | Other presumed ACM category | TBD |  |  |  |  | 0
UC-05 | Base Building | 05-5000 | Temporary structural support | LF |  |  |  |  | 0 | Need to define type of support
UC-06 | Base Building | 03-1000 | Sawcut, trench, backfill and patch slab | LF |  |  |  |  | 0 | Need to define slab type and thickness
UC-07 | Base Building | 03-1000 | Remove and replace concrete slab | SF | 14 | 6 | 1 | 2 | 23
UC-08 | Burlington | 03-3500 | Floor grinding / slab preparation | SF |  |  |  |  | 0
UC-09 | Joyful Garden | 09-3000 | Ceramic / porcelain wall tile installed | SF |  |  |  |  | 0
UC-10 | Joyful Garden | 09-9100 | Interior wall painting | SF | 4.5 |  |  |  | 4.5
UC-11 | Joyful Garden | 09-2000 | Metal stud / gypsum partition | SF |  |  |  |  | 0
UC-12 | Joyful Garden | 09-5100 | Acoustic specialty ceiling / cove grid | SF |  |  |  |  | 0
UC-13 | All | 55-0100 | Carpenter labor - regular time | HR | 98 |  |  |  | 98
UC-14 | All | 55-0100 | Carpenter labor - overtime | HR | 108 |  |  |  | 108
UC-15 | All | 55-0100 | Laborer - regular time | HR | 80 |  |  |  | 80
UC-16 | All | 55-0100 | Laborer - overtime | HR | 95 |  |  |  | 95
UC-17 | All | 55-0300 | Dumpster / disposal | EA | 0 | 995 |  | 90 | 1085
UC-18 | All | 50-1900 | Lift / hoisting equipment | DAY | 0 |  |  |  | 0

## Subcontractors
PROPOSED SUBCONTRACTORS AND MAJOR VENDORS
Identify proposed firms by trade. Boston Showcase is a required kitchen-equipment subcontractor/vendor.
Trade / Scope | Applicable Scope | Proposed Firm | Contact | Union / Open Shop | Required / National Account | Included in Bid? | Bid Coverage Status | Notes
Demolition | All | TBD - Need to fully scope and vet |  | Open Shop
Hazardous Materials Abatement | Base Building / Burlington | TBD - Need to fully scope and vet |  | Open Shop
Concrete | All | TBD - Need to fully scope and vet |  | Open Shop
Masonry | Base Building / Burlington | TBD - Need to fully scope and vet |  | Open Shop
Structural Steel / Misc. Metals | All | TBD - Need to fully scope and vet |  | Open Shop
Rough Carpentry | All | TBD - Need to fully scope and vet |  | Open Shop
Finish Carpentry / Millwork | Joyful Garden / Burlington | TBD - Need to fully scope and vet |  | Open Shop
Roofing | All | TBD - Need to fully scope and vet |  | Open Shop | Landlord-approved roofer if required
Doors / Frames / Hardware | All | TBD - Need to fully scope and vet |  | Open Shop
Specialty / Folding Partitions | Joyful Garden | TBD - Need to fully scope and vet |  | Open Shop
Glass / Glazing / Storefront | All | TBD - Need to fully scope and vet |  | Open Shop
Drywall / Metal Framing | All | TBD - Need to fully scope and vet |  | Open Shop
Acoustical / Specialty Ceilings | Joyful Garden / Burlington | TBD - Need to fully scope and vet |  | Open Shop
Flooring | Joyful Garden / Burlington | TBD - Need to fully scope and vet |  | Open Shop
Painting / Wall Covering | All | TBD - Need to fully scope and vet |  | Open Shop
Specialties | All | TBD - Need to fully scope and vet |  | Open Shop
Kitchen Equipment | Joyful Garden | Boston Showcase |  |  | Required subcontractor/vendor | Yes | Required
Fire Protection | All | TBD - Need to fully scope and vet |  | Open Shop
Plumbing | All | TBD - Need to fully scope and vet |  | Open Shop
HVAC | All | TBD - Need to fully scope and vet |  | Open Shop
Electrical | All | TBD - Need to fully scope and vet |  | Open Shop
Telecom / AV / Security | All | TBD - Need to fully scope and vet |  | Open Shop
Site / Civil | Base Building | TBD - Need to fully scope and vet |  | Open Shop
Landscape | Base Building | TBD - Need to fully scope and vet |  | Open Shop
Signage / Graphics | Base Building / Burlington | TBD - Need to fully scope and vet |  | Open Shop

## Q-A-E
QUALIFICATIONS / ASSUMPTIONS / EXCLUSIONS
List every qualification, assumption, and exclusion. Reference drawings, specifications, or addenda where applicable.
No. | Scope | Type | Drawing / Spec / Addendum Ref. | Description | Pricing Impact | Included in Base? | Proposed Resolution / Notes
1 | General / Contract | Qualification | N/A | See Separate attached qualifications | N/A | N/A | Owner to review
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Document Register
BID DOCUMENT REGISTER AND ACKNOWLEDGMENT
Acknowledge receipt of each listed document and all subsequent addenda.
Category | Document | Issue / File Date | Pricing Status | Received? | Reviewed? | Bidder Notes
Form of Contract | Draft A102-2017 and A201-2017 Construction Contract Documents | July 17, 2026 | Bid contract form | Yes | Yes
Project Schedule | Watertown Mall Project Schedule.pdf | July 17, 2026 | Preliminary; Invitation dates control | Yes | Yes
Phasing Plan | Watertown Mall_Phasing Diagram.pdf | July 17, 2026 | Preferred phasing basis | Yes | Yes
Hazardous Materials | Watertown Mall - HAZMAT Report 020226.pdf | February 2, 2026 | Bid and reference basis | Yes | Yes
Core Shell and Site | Watertown Mall Base Building Drawings.pdf | July 8, 2026 | Construction-document pricing set | Yes | Yes
Core Shell and Site | Watertown Mall Site Drawings.pdf | July 1, 2026 | Issued for Bid | Yes | Yes
Core Shell and Site | Watertown Mall Site Specs.pdf | July 1, 2026 | Issued for Bid | Yes | Yes
Core Shell and Site | Watertown Mall Target Responsibility.pdf | July 17, 2026 | Scope coordination document | Yes | Yes
Joyful Garden | Joyful Garden Draft CDs.pdf | July 3, 2026 | Base pricing set pending addendum | Yes | Yes
Joyful Garden | Joyful Garden Draft CDs Tenant Comments.pdf | July 2026 | Anticipated revisions; not standalone set | Yes | Yes
Joyful Garden | Joyful Garden Draft CDs Landlord Comments.pdf | July 2026 | Anticipated revisions; not standalone set | Yes | Yes
Joyful Garden | Folding Panel Plans and Specs folder | May 21, 2026 | Pricing basis | Yes | Yes
Burlington | Burlington Coat Factory Prototype.pdf | Current folder version | Conceptual pricing basis | Yes | Yes
Burlington | Burlington Coat Factory Spec Book.pdf | Current folder version | Conceptual pricing basis | Yes | Yes
Burlington | Burlington Coat Factory Facade and Sign Concept.pdf | Current folder version | Conceptual pricing basis | Yes | Yes
Burlington | Tenant Work Letter / Exhibit C | To be included | Conceptual pricing basis | Yes | Yes
Record Drawings | Architectural, Structural, MEP and Target Record Drawings | Various | Reference only; field verify | Yes | Yes
Addenda | Addendum No. 1 | Anticipated July 24, 2026 | When issued | Yes | Yes
Addenda | Addendum No. 2 |  | When issued | Yes | Yes
Addenda | Addendum No. 3 |  | When issued | Yes | Yes

## Schedule-Logistics
PRELIMINARY SCHEDULE AND LOGISTICS
Provide bidder-proposed milestones and concise narratives. Attach a detailed CPM schedule and logistics plan.
Key Milestones
Milestone | Owner Preliminary / Required Date | Bidder Proposed Start | Bidder Proposed Finish | Duration (Calendar Days) | Notes / Assumptions
Notice to Proceed / Mobilization
Separate Demolition Permit Submitted
Full Building Permit Submitted
Target Mall-Entry Closure Complete | 2026-10-15 |  |  |  | Required completion date
Core & Shell / Site Construction Start | 2026-09-28 |  |  |  | Preliminary project schedule
Joyful Garden Fit-Out Start | 2026-12-28 |  |  |  | Preliminary project schedule
Joyful Garden Substantial Completion
Burlington Construction Start | 2027-06-21 |  |  |  | Preliminary project schedule
Burlington Substantial Completion
Overall Project Completion | 2028-05-26 |  |  |  | Preliminary project schedule
Required Logistics Narrative
Topic | Bidder Narrative / Approach | Cost or Schedule Effect
RMV access route | Maintain safe, lit, dust-free route from active mall entrance to RMV entrance, adjacent restrooms, and back-of-house facilities. | See web based proposal
Existing Joyful Garden operations | Describe protection, access, deliveries, shutdowns, and transition sequencing. | See web based proposal
Mall corridor phasing | Address north/south phasing around primary skylight and occupied mall conditions. | See web based proposal
Dust / noise / vibration control | Describe temporary partitions, negative air, monitoring, cleaning, and off-hours work. | See web based proposal
Fire / life safety | Describe egress, alarms, sprinklers, fire watch, emergency access, and AHJ coordination. | See web based proposal
Deliveries / staging / storage | Identify loading, laydown, hoisting, delivery hours, and storage assumptions. | See web based proposal
Target entry closure | Describe permit sequence, temporary protection, demolition, construction, inspections, and schedule contingency. | See web based proposal
Temporary utilities | Describe temporary power, lighting, heat, ventilation, water, and shutdown coordination. | See web based proposal
Hazardous materials | Describe abatement sequencing, containment, monitoring coordination, and restoration. | See web based proposal
Off-hours work | Identify work assumed to occur nights/weekends and included premium. | See web based proposal

## Bid Summary
BID SUMMARY
One combined GMP under a single contract with three separate schedules of values.
Bidder and Proposal Information
Bidder Company | New England Construction
Adam Aresenault | Adam Arsneault
aarsenault@neconstruction.com | aarsenault@neconstruction.com
2026-08-14 | 2026-08-14
2026-09-14 | 2026-09-14
GMP Summary by Scope
Pricing Component | Base Building | Joyful Garden | Burlington | Combined GMP
Direct Trade Cost | 2712317 | 4271716 | 2374267 | 9358300
GC / GR Allocation | 286421.24 | 277457 | 237849.76 | 801728
Subtotal Before Contingency and Markups | 2998738.24 | 4549173 | 2612116.76 | 10160028
Pricing / Design Contingency Rate | 0% | 0% | 0% | 0%
Pricing / Design Contingency | 0 | 0 | 0 | 0% | 5% by LL
GMP / Construction Contingency Rate |  |  |  | 0%
GMP / Construction Contingency | 0 | 0 | 0 | 0 |  | Removed for Stip Sum agreement
SDI / Subcontractor Bonds Rate | 0% | 0% | 0% | 0% | 1.5% if elected by owner
SDI / Subcontractor Bonds | 0 | 0 | 0 | 0%
Insurance Rate | 1.912% | 1.92% | 1.918% | 1.917%
Insurance | 57350.8688 | 87344.1216 | 50087.3389 | 194782.3293
Contractor Fee Rate | 3.533% | 3.535% | 3.535% | 3.534%
Contractor Fee | 107956.3478 | 163900.8802 | 94108.9149 | 365966.1429
Building Permits and Fees | 25605 | 24795 | 50760 | 101160
Other Markup / Cost |  |  |  | 0
Base Project Scope Total | 3189650.4566 | 4825213.0018 | 2807073.0138 | 10821936.4722
Potential Additional Target Scope |  |  |  | 108810
Potential Project Total |  |  |  | 10930746.4722
Included Allowances (informational) | 123650 | 872059 | 63000 | 1058709
Proposal Completeness Check
Three SOVs Complete |  |  | Complete
GC / GR Allocation Balanced |  |  | Complete
Allowances Entered |  |  | Complete
Subcontractor List |  |  | Complete
Document Register |  |  | Complete
Bidder Certification
The undersigned certifies that the proposal includes all labor, materials, equipment, supervision, coordination, permits, temporary conditions, insurance, bonds, fee, contingencies, allowances, and other costs required by the bid documents, except only as expressly identified on the Q-A-E tab. The bidder acknowledges that the project will be awarded under one contract and that the three pricing components are not separately awardable.
Authorized Signatory
Title
Date