## 1-A General Conditions
Boston University
ITB Attachment 1-A - General Conditions Breakdown
BU Pergande Lab Renovation
|  |  | Construction |  |  | Close out
| Position/Name | Hourly Rate | July | Aug. | Sept. | Month | Total
Example | Project Manager | 100 |  |  |  |  | 0
| Jim Jones | [5 empty] | 0
1 | Project Manager | 90 | 48 | 48 |  |  | 96
| Rob McLean | [5 empty] | 8640
2 | Project Engineer | 70 | 48 | 48 |  |  | 96
6720
3 | Superintendent | 95 | 160 | 160 |  |  | 320
| Cameron Tetreault/ Christian Mascaro | [5 empty] | 30400
4 | General Superintendent | 150 | 8 | 8 |  |  | 16
| Luke Grady | [5 empty] | 2400
5 | Construction Manager | 75 | 8 | 8 |  |  | 16
1200
6 | Safety Manager | 100 | 8 | 8 |  |  | 16
| Joseph Teixeira | [5 empty] | 1600
7 | Accounting | 85 | 4 | 4 |  |  | 8
680
8 | Position | 0 |  |  |  |  | 0
| Name | [5 empty] | 0
9 | Position | 0 |  |  |  |  | 0
| Name | [5 empty] | 0
| Total General Conditions | [5 empty] | 51640

## 1-B General Requirements
Boston University
ITB Attachment 1-B - General Requirements Breakdown
BU Pergande Lab Renovation
Description | Cost per Week | No. of Weeks | Total Cost
Mobilize/Demobilize |  |  | N/A
Temporary Utilities & Facilities |  |  | N/A
Reproduction - Drawings/Printing |  |  | N/A
Project Temporary Signage |  | 8 | 750
Mail/Postage |  |  | N/A
Field Computers/Software |  |  | N/A
Field Office Supplies |  |  | N/A
Field Office Equipment |  |  | N/A
Field Office Furniture |  |  | N/A
Misc. Supplies - |  |  | 17631 | General Labor: $760 Dumpsters (Live Load): $8500 Total Barriers & Enclosures (Temp. Protection): $4500 Total Final Cleaning: $3000 Total Building Permits: $871 Bagging Permit: $500
Cellphones - Field Personnel |  |  | Included
Parking |  |  | N/A
Safety Equipment& Signage |  |  | Included
| TOTAL |  | 18381