## SOV Template
Apartments on Oaklawn Avenue
Base Bid Schedule of Values
Description | Cost | Comments
Div 01 - General Conditions
General Requirements | 365098
Div 02 - Demolition | NOT APPLICABLE | N/A
Div 02 - Sitework
Building E&B | 66658 | Included fences, dumpster enclosure
Underground Utilities within Building | INCLUDED | Included
Hardscape Lansdscape | BY OWNER | by owner
Irrigation | BY OWNER | by owner
Div 03 - Concrete
Foundations | 74314
Concrete Slabs | 56193 | Includes sog, sidewalk, porch stoops, aprons and dumpster enclosure
Cementitious Decks and Underlayment | 23500
Div 04 - Masonry
Stone and Brick Veneer | 185250
Kitchen and Vanity Stone/Quartz Tops | 47492 | Includes curb cap @ shower
Div 05 - Metals | 34602
Div 06 - Wood and Plastics
Rough Carpentry | 531314
Finish Carpentry | 26052
Div 07 - Thermal and Moisture Protection
Rigid Insulation | 5567 | Foundation wall insulation only
Batt Insulation | 158700
Roofing | 61066
Composite Siding & Azek Trim | 198639
Deck and Rail Systems | 39627
Gutters and Downspouts | Included
Firestopping | 3000
Div 08 - Doors and Windows
Andersen 400 Windowns and Patio Doors | 136531
Bldg Front Doors - Andersen Straightline | 28969
Interior Solid Core Wood Doors | 133229 | Includes all hardware and taxes
Hollow Metal Doors and Frames | 10900 | Hardware and tax not included
Thermacore Garage Overhead Doors | 15969
Frameless Shower Doors | 12600
Louvers | 2275
Door and HW installation | 32800
Div 09 - Finishes
Bathroom Tile | 58500
Apartment LVT Flooring | 111500
Common Area Flooring, Stairtreads and Mats | 4350
Blueboard and Plaster OR GWB/Taping Level 5 | 319500 | Only included in living areas/corridors. NIC in garges and closets.
Interior Painting | 45000
Exterior Painting | 16026
Floor prep | 5025
Div 10 - Specialties
Bathroom Accessories & Mirrors | 3379
Closet Wire Shelving | 4950
Fire Extinguishers and Cabinets | 1390
Mailbox Kiosk | 2400
Div 11 - Equipment
Appliances | NOT INCLUDED | Furnished by Owner
Div 12 - Furnishings
Kraftmaid Cabinets | 122325
Div 13 - Special Construction | NOT INCLUDED | N/A
Div 14 - Conveying Systems | NOT INCLUDED | N/A
Div 15 - Mechanical
Fire Protection | 65938
Plumbing | 300000
Plumbing Fixtures | NOT INCLUDED | Furnished by Owner
HVAC | 398000
Div 16 - Electrical
Electrical | 323600
Lighting Fixtures | AS NOTED | Furnished by owner w/exception of 5" LED Cans
Fire Alarm | INCLUDED
Subtotal | 4032228
Overhead/Profit | 163845
Insurance | 63900
Total | 4259973
Grand Total | 4259973
$/sf based on 16,413 SF | 259.5487

## Exterior Deduct Alts
Apartments on Oaklawn Avenue
Exterior Alternates
Description | Cost | Comments
EXTERIOR ALTERNATES
Specified PVC TRIM
Supplement Specified Azek Trim with Royal PVC Trim or Equal | TBD
Siding West Elevation (Rear of Building)
Supplement Specified Stone/Brick Veneer with E2 (Composite Lap Siding) | TBD
Supplement Specified Stone/Brick Veneer & E2 Composite Siding with Clapboard Vinyl Siding | TBD
Siding North and South Elevations (Sides of Building) | TBD
Supplement Specified Brick Veneer Water table with E2 (Composite Lap Siding) | TBD
Supplement Specified E2 (Composite Lap Siding) & Brick Veneer Water Table with Clapboard Vinyl Siding | TBD
Siding East Elevation (Front of Building)
Supplement Specified E2 (Composite Lap Siding) with Cedar Shake Vinyl Siding | TBD
Deck and Rail Systems
Supplement Specified Trex Decking and Timbertech Rail Systems with a similar but more cost efficient Deck and Rail Product | -3109 | Wolf Decking
``
Supplement Specified Andersen 400 Windows and Doors with Andersen 200 Series | -20299
Supplement Specified Andersen 400 Windows and Doors with Andersen Silverline Series (or equal) | TBD
2 - Bldg Front Doors - Supplement Specified Andersen Straightline with Therma-tru (or equal) | TBD
8 - Garage OH Doors - Supplement with HAAS or Equal | -3337 | Wayne Dalton 9605 Garage doors
Supplement Ben Moore w/Sherwin Williams Promar 200 | NO COST

## Interior Deduct Alts
Apartments on Oaklawn Avenue
Interior Alternates
Description | Cost | Comments
INTERIOR ALTERNATES
Deduct Interior Trim Package Labor and Materials | -25376
Deduct Interior Door Package Labor and Materials | -75400 | Includes Unit entry doors
Supplement specified Kraftmaid Cabinets with Wolf, JSI, Cabtec or Equal | -54443
Deduct to eliminate labor for Cabinet and Vanity Installation | -11300
Alternate to change Rubber Base to 7-1/4 Wood Base | TBD
Supplement Ben Moore w/Sherwin Williams Promar 200 | No Charge